Appendix B – Action plan 2025-2028
Ref	Action	Aim	Evidence of Impact	Action owner	Start and End date	Theme	TALENT recommendation
1	Review the Faculty Technical Lead role (FEPS/FELS/FMED/FAH) to ensure it remains relevant, effective, and aligned with organisational strategic objectives at institutional and faculty level.	Aligning the faculty’s technical lead roles with current needs to support the implementation of the Technician Commitment across the University and faculties.	Success of cross-faculty collaboration initiatives (coordinate approach to engagement, mentoring and skill exchange initiatives). Timely delivery of action plan/submission (engagement and TCIG owned actions).	TCIG ADI/Academic Lead Technical Lead	Q1-Q2 2025	Visibility Recognition Career Development Sustainability	Take a strategic approach to the sustainability of technical skills and careers, and appropriate succession planning through horizon scanning and identifying current and potential future skills gaps. Appoint an institutional strategic lead, e.g. Director of Technical Skills, to lead this agenda.
2	Development of the Technician Commitment support role to drive engagement through existing platforms (Hub, Microsite, Inbox, newsletter).	To ensure a coordinated approach to the Technician Commitment communication and engagement activities to support the delivery of our commitment and objectives.	Comms plan with clear metrics attached. Comms plans objectives are met. The Tech Commitment platforms will be updated regularly. Communication resources will be developed.	Sponsor EDI Team	Q1-Q2 2025	Visibility	Ensure considered inclusion of technical staff within all relevant communication channels and initiatives.
3	Develop and implement yearly communication and engagement plan with clear metrics attached to measure impact of the engagement.	To adopt a proactive approach to communication and engagement.	Successful delivery of communication and engagement plan (timeframes and targets) Increased participation in Technician Commitment activities.	HR EDI Team Technician Commitment support role	Q1-Q2 2025	Visibility	Support outreach and public engagement activities regarding technical careers in local schools and colleges to increase visibility of technical career opportunities to young people.
4	Implement a coordinated approach to gathering information from technicians across all faculties and platforms, aligning "Voice of the Technicians" with institutional and local surveys.	To gather comprehensive and consistent data from technicians across all faculties to assess their feedback and improve program effectiveness.	Enhanced decision-making Better resource allocation Action plan effectiveness	TCIG ADI/Academic Lead Technical Lead	Q3-Q4 2025	Visibility Recognition Career Development Sustainability	Be inclusive of technical staff and their considerations in conversations on sector-policy developments. Support technical staff to contribute to and/or attend government events and initiatives to develop policy.
5	Automate the welcome process for new TAE starters to ensure they receive relevant information specific to them about the Technician Commitment and other EDI Charters	To welcome new technical staff and bring them up to speed with our commitment to our technical community.	Visiting rates for the page and opening of the email. New starters questionnaire scores high for TAE staff in the relevant questions. Early engagement with the Hub and relevant activities.	HR EDI Team	Q1-Q2 2025	Sustainability	Ensure considered inclusion of technical staff within all relevant communication channels and initiatives.
6	Promote CHEP’s comprehensive provision to support continuous professional development for technicians ensuring awareness and accessibility of the relevant training and resources.	Increase awareness of CHEP provision among technicians, ensuring CHEP’s comprehensive offer is fully utilised, leading to a more skilled and cohesive technical workforce.	Track career progression of technicians to correlate training and coaching with career advancement.	CHEP	2025 -2027	Career Development	Technical staff should engage positively with current and future opportunities that are available to them
7	Facilitate access to existing Research Funding Development (RFD) resources and supporting structures to enhance technicians’ understanding of the funding landscape and improve their grant application skills.	Equip Technicians with the knowledge and skills needed to effectively identify, apply for, and secure relevant grants.	Increased number of TAE attending grant funding training and accessing RFD resources. Increased number of technical staff submitting grant applications. Positive feedback from technicians on the usefulness of the resources and support provided.	RIS - RFD	2025 -2027	Recognition	Ensure the contributions of technical staff are visible and recognised Enable opportunities for technical staff to be considered as co-investigators, co-supervisors, for grants or projects.
8	Analyse uptake for existing CHEP, HR LMD, and Faculty/School training offers, assess faculty-specific investments, to provide data-driven recommendations for future faculty training allocations.	To enhance the effectiveness and relevance of training and development opportunities for TAE employees.	Increased training uptake Improved performance/progression metrics Reduced turnover rates	TCIG ADI/Academic Lead Technical Lead	Q1 - Q2 2025	Career Development	Technical staff should engage positively with current and future opportunities that are available to them
9	Introduce a framework to enable technicians to create sustainable forums to connect, share best practices, and develop knowledge in specific areas of their professional practice.	To equip technicians with the necessary tools and techniques to form effective knowledge sharing and collaboration systems.	Informative sessions attendance numbers. Areas of Interest and volunteers identified. Self-managed forums are in place. Feedback from identified participants.	TCIG CHEP	Q3 2025 - 2027	Career Development Sustainability	Strategic approach to ensure the sustainability and appropriateness of technical skills and careers, at both a local and national level (Training and development)
10	Identify mentors at all levels across the university and collaborate with local initiatives (faculties and schools) to ensure visibility and promote mentoring for technical staff.	To align with existing mentoring initiatives to maximise resources available while offering suitable mentoring opportunities to technical staff.	Increase in the number of mentors Mentoring programmes available to technical staff. Feedback from identified mentees & mentors.	ADI & Faculty Academic Leads	Q3 2025	Career Development Sustainability	Strategic approach to ensure the sustainability and appropriateness of technical skills and careers, at both a local and national level (Training and development)
11	Integrate TAE in the UoS Talent Plan rollout across all faculties, including overhauling the Super Recruiter (SR) program, as outlined in the “University of Southampton Talent Plan Strategy" 2024-2030.	Implement the University of Southampton Talent Action Plan across the TAE job family to attract, develop, retain, and maintain a diverse and high-performing workforce.	Successful roll out of succession planning across TAE. Increase in the number of quality candidates applying for positions at the University of Southampton. TAE participation in Super recruitment programme. Positive feedback from candidates regarding the recruitment process. Increase in employee satisfaction and engagement scores related to learning and development opportunities. Improvement in performance metrics attributed to employee skill enhancement and development efforts. Build confidence of our Leaders and Managers to effectively manage both high performing staff and staff who require development. Retain: Tracking of areas of high turnover, with underpinning investigation into why they exist. Tracking of Internal/ external applicants for opportunities. Positive feedback from employees regarding workplace culture, recognition, and opportunities.	HR Talent & Resourcing HR LMD HRBPs	2024 -2030	Career Development Sustainability	Take a strategic approach to the sustainability of technical skills and careers, and appropriate succession planning through horizon scanning and identifying current and potential future skills gaps.
12	Promote line management tools to support the effective management of TAE staff, recognising the unique responsibilities and expectations of TAE roles compared to other job families.	Enhance the management of TAE staff by raising awareness of line management tools.	Improvement in the quality of appraisals for TAE staff. Improvement in scores of key indicators for TAE staff (job satisfaction, retention rates, progression, recognition, and progression).	HR LMD	Q3 2025 Q3 2026 Q3 2027	Career Development	Ensure provision and protected time for training and professional development, supporting technical staff to take advantage of development opportunities, such as technical training, placements, and/or professional registration. Define a minimum yearly allowance of days for technical staff to undertake professional development.
13	Review how TAE staff are engaging with the new "unpaid career breaks" policy to understand how technicians are using it to engage in professional development opportunities.	Foster a culture of continuous learning and professional development among TAE staff at the UoS, while also ensuring the university’s operational efficiency and effectiveness.	Number of TAE eligible employees taking career breaks for personal development. Acquisition of skills or certifications obtained by employees during their breaks. Increased employee satisfaction.	HR R&R	2026 - 2028	Career Development	Take a strategic approach to the sustainability of technical skills and careers, and appropriate succession planning through horizon scanning and identifying current and potential future skills gaps.
14	Implement a skills exchange programme to provide opportunities for learning and development (job shadowing, job swap, or similar) for TAE.	Foster a culture of continuous learning and professional development among TAE staff at the UoS, while also ensuring the university’s operational efficiency and effectiveness.	Increased number of opportunities Job satisfaction Retention Strengthen links with other departments and institutions (joint projects/collaboration).	TCIG HRBP	2025 -2028	Career Development Sustainability	Take a strategic approach to the sustainability of technical skills and careers, and appropriate succession planning through horizon scanning and identifying current and potential future skills gaps. Ensure provision and protected time for training and professional development, supporting technical staff to take advantage of development opportunities, such as technical training, placements, and/or professional registration. Define a minimum yearly allowance of days for technical staff to undertake professional development.
15	Rewrite the apprenticeship guidance to address current gaps and inefficiencies in the guidance and to further align with organisational goals.	To improve apprenticeship outcomes and the support of workforce development by aligning with evolving organisational goals.	Improved feedback from hiring managers.	HR R&R	2025 -2026	Sustainability	Expand entry routes to technical roles and careers by encouraging applicants from both vocational pathways and academic pathways Invest in apprentices and trainee technician positions, hosting placements for qualifications (e.g. T-Levels in England) and work experience placements for local schools and colleges. Utilise the Apprenticeship Levy for training and developing technical staff.
16	Socialise the re-written TAE job family and guidance following the introduction of a TAE L6 Grade and the completion of the Career Pathway Refresh Project.	To inform stakeholders and help them understand the new TAE L6 Job Description and the refreshed Career Pathway to improve role clarity, career development opportunities, and career progression routes.	Changes on the distribution of employees by grade (flatten distribution - Number of TAE L6 roles). Improved progression rates across the board. Sustained job satisfaction indicators. Improved score at Research Culture Survey Pilot (or similar indicator).	HR R&R HRBP	2025 -2026	Recognition	Visibility of clearly defined career pathways and progression routes, with accurate and standardised job descriptions for technical roles. Support the development and implementation of a new, simple, and fit-for purpose classification for technical roles in higher education, research, and innovation at all levels, such as by creating a new job family specifically for technical roles, separate from academic, administrative, or any other job family.
17	Document the positive impact on visibility, research culture, policy implementation, and collaboration of having technician representation on institutional and faculty committees.	To increase TAE visibility and recognition by evidencing the positive impact of having technician representation on institutional and faculty committees.	Success of cross-faculty collaboration initiatives. Instances where technician input significantly influenced committee outcomes.	TCIG ADI/Academic Lead Technical Lead	2025 - 2027	Recognition	Ensure representation of technical staff on department-, faculty-, and institution-level decision-making committees, boards, panels, and similar groups, through either a dedicated seat or designated technical advocates within senior leadership and/or existing members. This includes processes and committees to develop institution-wide strategies and long-term goals.
18	Develop a standardised process to ensure the contributions Technicians make to teaching and supporting students are considered when completing the TEF return for the university.	To ensure technical staff are appropriately recognised for their contribution to education.	Technicians are explicitly mentioned in TEF	TEF development team	2026 -2029	Recognition	Review how staff contributions are recognised and rewarded at department- and institution-level, and whether inclusivity exists across all job families.
19	Design and implement a process to document the contributions of technicians to research at institutional and unit of assessment level.	To ensure technical staff are appropriately recognised for their contribution to research.	Increased number of publications acknowledging technicians’ contributions recorded. Technicians are explicitly mentioned in REF.	RIS Library	2026 - 2029	Recognition	Review how staff contributions are recognised and rewarded at department- and institution-level, and whether inclusivity exists across all job families. Encourage appropriate inclusion of technical staff as authors, co-authors, or contributors on published papers and presentations.
20	Develop a programme of work supporting technicians to deepen their understanding in research integrity and trusted research awareness through structured and collaborative efforts.	To enhance technicians understanding of research integrity and trusted research topics, while enabling them to participate in shaping key policies through structured and collaborative initiatives.	Participation on awareness and training sessions. Contribution and policy feedback participation. Success stories technicians apply learned best practices in their research activities. Improvement on Research Culture Survey score (TBC).	RICO	2025 - 2028	Career Development Visibility	Ensure representation of technical staff on department-, faculty-, and institution-level decision-making committees, boards, panels, and similar groups, through either a dedicated seat or designated technical advocates within senior leadership and/or existing members. This includes processes and committees to develop institution-wide strategies and long-term goals.
21	Establish a collaborative partnership between the Researcher Development Concordat & Technician Commitment to address the shared goals of promoting professional development and ensuring recognition and inclusion both groups.	To enhance the collaboration between the Researcher Development Concordat and the Technician Commitment, creating a holistic approach to research culture that fosters a supportive and inclusive environment.	Growing changes influenced by joint advocacy. Increase of collaborative projects and initiatives launched. More frequent joint meetings and workshops. A greater number of cross-functional training sessions conducted. Surging joint publications and research outputs.	RDC TCIG	2025 - 2028	Visibility Recognition Career Development Sustainability	Ensure representation of technical staff on department-, faculty-, and institution-level decision-making committees, boards, panels, and similar groups, through either a dedicated seat or designated technical advocates within senior leadership and/or existing members. This includes processes and committees to develop institution-wide strategies and long-term goals.
22	Engage with TAE staff and the TCIG, ensuring the voices of technicians are heard and their recommendations integrated into the Reducing Casualisation project’s framework.	To reduce casualisation at the University of Southampton, thereby enhancing job security, promoting fair employment practices, and making the University an employer of choice.	A reduction in % of TAE FTC staff. Improved uptake of redeployment opportunities. Lower staff turnover and higher talent retention. Improvement in survey scores and engagement.	Reducing Casualisation Project	2024-2028	Career Development Sustainability	Take a strategic approach to the sustainability of technical skills and careers, and appropriate succession planning through horizon scanning and identifying current and potential future skills gaps.
23	Investigate and analyse the approaches taken by other institutions in relation to Research Technical Professionals.	To understand the role and recognition of Research Technical Professionals in other institutions, and how this may inform usage of Southampton's current job families and career pathways.	Conduct a Russell Group desk review and engage with representatives from different institutions. Gather insights and best practices from each institution. Set of clear, actionable recommendations.	HR R&R TCIG	2025 - 2027	Career Development Sustainability	Enable opportunities for technical staff to be considered as co-investigators, co-supervisors, for grants or projects. Support the development and implementation of a new, simple, and fit-for purpose classification for technical roles in higher education, research, and innovation at all levels.
24	Identify and understand the extent our Research Technicians Professionals (RTPs) cohort to inform decision-making and ensure existing recognition mechanisms are effective, equitable, and aligned with career development pathways.	A well-defined RTP classification that strengthens RTP research activities, supports career development, and contributes to the university’s research objectives.	Evidence-base decision making / informed decision. Improved employee satisfaction indicators.	HR R&R TCIG	2025 - 2027	Career Development Sustainability	Enable opportunities for technical staff to be considered as co-investigators, co-supervisors, for grants or projects. Support the development and implementation of a new, simple, and fit-for purpose classification for technical roles in higher education, research, and innovation at all levels.

Abbreviations
ADI	Associate Dean Infrastructure
CHEP	Centre for Higher Education Practice
EDI	Equality Diversity and Inclusion
FAH	Faculty of Arts and Humanities
FELS	Faculty of Environmental and Life Sciences
FEPS	Faculty of Engineering and Physical Sciences
HR	Human Resources
HRBP	Human Resources Business Partner
LMD	Leadership and Management Development
MED	Faculty of Medicine
R&R	Reward and Recognition
REF	Research Excellence Framework
RFD	Research Funding Development
RICO	Research Integrity and Compliance Office
SR	Super Recruiter
TAE	Technical and Experimental
TEF	Teaching Excellence Framework

Definitions & Meaning
Faculty Technical Leads	Introduced in April 2020 to have strategic oversight of technical skills across the University; lead on the implementation of the University’s Technician Commitment and represent technical staff at management and University committees where appropriate. Four technical leads (each at 0.2 FTE).
UoS Talent Programme	The purpose of the UoS Talent Plan is to attract, develop, retain, and maintain a diverse and high-performing workforce. Key elements include developing a resourcing plan, employer branding, talent, candidate attraction, new employee pipelines, career advice, and targeted recruitment support to line managers.
Super Recruiter	Trained members of staff who will highlight key ‘touchpoints’ in the recruitment process where inclusion should be considered and advocate for inclusive recruitment practices throughout the process.
Research Culture Landscape Survey	Developed in 2023-2024 by Vitae and piloted with nine HEIs. It gathers views on research culture in UK institutions.
Hub	UoS Technician’s SharePoint page with resources to support technical staff working at the UoS.
Voice of Technicians	Survey of technicians at UoS to gather feedback on work and delivery of TCIG action plan.